## Sheet1
Focus Area | Sl No | Task | September | October | November | Dec | Jan'25 | Feb'25 | Mar'25 | Apr'25 | Remark (18th Nov'24) | Action Required to Close |  | Completed
Organisation Structure and Design | 1.1 | Assess Organizational Goals and Needs, Review of "As Is" Org. Structure: ○ Understand the company's mission, goals, and strategic objectives. ○ Identify the functions, roles, and departments required to achieve those objectives. | [11 empty] | Onhold/pending
| 1.2 | Define Reporting Relationships: ○ Determine the hierarchy of authority and reporting lines by sitting 1 on 1 with the dept. ○ Specify how decision-making flows and who is accountable to whom. | [9 empty] | ON Hold |  | WIP
| 1.3 | Choose the Right Structure: ○ Select the appropriate organizational structure (e.g., Geographical, functional, divisional, cross functions, matrix, flat), along with grades and bands ○ Consider factors like company size, industry, and communication requirements. ○ Conduct the "Fit Tests" and "Good Design Tests" to ascertain the right structure. | [9 empty] | ON Hold |  | Plan
| 1.4 | Identifying the unique roles, desgination restructring, combine the designations based on the work of the organization | [8 empty] | Work under progress |  |  | New addition
| 1.5 | Scripting Job Descriptions for leadership team.
| 1.6 | Scripting Job Descriptions for the Unique Roles (1 -on -1 meeting to explain job requirement)
| 1.7 | Mapping Job grades and bands : Market research to understand the trend Align the trend with the new proposed structure and script the grades and bands
| 1.8 | Town Hall to Communicate Organisation Structure
POSH Implementation | 2.1 | Source POSH trainers - Arrange for intial meet - Get quotation - Agree on the terms and conditions - Set Expectations | [10 empty] | New addition
| 2.2 | Know the necessary actions for compliance, including setting up an Internal Committee (IC), creating awareness, and instituting reporting procedures
| 2.3 | Monitor and ensure that IC members are trained in handling sensitive issues and conducting inquiries objectively and impartially
| 2.4 | Create awareness by posting reminders on the company’s internal platforms, such as email newsletters or notice boards | [9 empty] | Recurring Activity
| 2.5 | Conduct refreshers every quarter - check for records - Get the reports from the external trainer
| 2.6 | Establish a system for tracking complaints and resolutions. Keep records of incidents reported, investigations conducted, and outcomes achieved
Develop the P2P SOP | 3 | Structured Business Requirement sessions and management discussions with Senior Management and respective key stakeholders
| 3.1 | Develop a detailed SOP outlining each step of the procure-to-pay process
| 3.2 | Review the SOP with relevant stakeholders to ensure clarity and accuracy.
| 3.3 | Train employees on the SOP and drive the implement it across the organization.
HRMS system implementation and Practice | 4.1 | Understand the "As is" of the HRMS system in place | [10 empty] | New addition
| 4.2 | Meeting with Vendor to understand the feature , reports, dashboards in specific to the active modules
| 4.3 | Identify the requirement and share with the vendor, for full fledged usage of active modules
| 4.4 | Capture employee information (Group companies) on the HRMS system - As part fo the feed for Dashboard
| 4.5 | Phase I : Streamline recruitment and onboarding process - implement MRF & IEF as a practice
| 4.6 | Phase II : Map reporting structure, Leave management & Exit process
| 4.7 | Phase III : Streamline PMS & Review process
| 4.8 | Phase wise train the employees, managers & conduct refresher sessions
Talent Acquisition Process | 5.1 | Recruitment Process: Understand the "As is". Defined - Position, Approvals, Advertisement, Interviewing Process, Interview Panel, Reference Check, Compensation Fitment
| 5.2 | Realign the recruitment process inorder to improve, fasten and track the complete process. Implement the process and measure the impact
| 5.3 | Created a robust Recruitment SOP | [10 empty] | New addition
| 5.4 | Conduct workshop for Hiring Manager on Structured Interview Process
| 5.5 | Refresh the Onboarding and New-Hire processes to align with business goals
| 5.6 | Refresh Induction program (+OJT) to align with business requirement
| 5.7 | Implementation of Onboarding and Induction Program in the Business
Develop the R2R SOP | 6.1 | Structured Business Requirement sessions and management discussions with Senior Management and respective key stakeholders
| 6.2 | Develop a detailed SOP outlining each step of the record -to- report process | [8 empty] | As is process captured and aligned
| 6.3 | Review the SOP with relevant stakeholders to ensure clarity and accuracy. | [8 empty] | Review to be done by 08-11-24
| 6.4 | Train employees on the SOP and drive the implement it across the organization. | [8 empty] | To be conducted in 3rd week of November
Performance Management System | 7.1 | Understand the PMS "As is". Check records of the reviews done so far
| 7.2 | Designing Performance Management Framework (Approach for current year appraisal)
| 7.3 | Goals Scripted for Leadership Team (Both What & How aspect of deliverables)
| 7.4 | Goals Scripted for Identified Roles & Individuals
| 7.5 | Introducing continuous Monitoring framework to team for performance review
| 7.6 | Implementing Performance Management - basis defined role and goals scripted for next Level of Managers
| 7.7 | Train Managers to conduct impactful one on one process
| 7.8 | Facilitating Monthly 1-on-1 Meeting with Respective Managers
| 7.9 | Defining process for Year end Review
| 7.1 | Training Managers on "How to conduct Objective Review
| 7.11 | Review conducted as per schedule (Weekly, Monthly and Quarterly)
Develop the O2C SOP | 8 | Structured Business Requirement sessions and management discussions with Senior Management and respective key stakeholders
| 8.1 | Develop a detailed SOP outlining each step of the order to cash process
| 8.2 | Review the SOP with relevant stakeholders to ensure clarity and accuracy.
| 8.3 | Train employees on the SOP and drive the implement it across the organization.
HR Policy & Process | 9.1 | Review of Exisitng Policies & Processes
| 9.2 | Realignment of policies to support Organization goals | [9 empty] | 2 policy rollout per month /24
| 9.3 | Develop HR Policies and get approved, update it on the HRMS system and the induction deck
| 9.4 | Townhall organised to introduce refreshed policies
| 9.5 | Reviewthe implementation and conduct refresher sessions
Develop the DOA SOP | 10 | Structured Business Requirement sessions and management discussions with Senior Management and respective key stakeholders
| 10.1 | Develop a detailed SOP outlining each step of the delegation of authority process
| 10.2 | Review the SOP with relevant stakeholders to ensure clarity and accuracy.
| 10.3 | Train employees on the SOP and drive the implement it across the organization.
Business Intelligence ¦ MIS Framework | 11 | Discuss current reporting processes, pain points, and desired outcomes (profitability analysis by different level, cost allocation) with Senior Management & Respective Key Stakeholders
| 11.1 | Conduct interviews with stakeholders to understand current challenges and desired functionalities
| 11.2 | Identify data sources (ERP, CRM, HRIS, Other Standalone Data Sources).
| 11.3 | Evaluate the quality, consistency, and level of detail of the data, including aspects like line of business, geographical regions, sales person & product categories, etc
| 11.4 | Assess the completeness, accuracy, and timeliness of data relevant to profitability metrics
| 11.5 | Develop a plan to ensure integrity of data going forward
| 11.6 | Developing KPIs that drive deliverables, growth and OKRs
Business Analytics ¦ Dashboarding | 12 | KPI Definition and Benchmarking
| 12.1 | Develop a mock Dashboard with Data Provided | [9 empty] | The definitions of certain datapoints needs to be cleared out with the respective stakeholders
| 12.2 | Develop a robust data model integrating all the data sources
| 12.3 | Align the mock dashboard with key stakeholders and refine the necessary changes to be made | [9 empty] | The neccessary filters, visuals and KPIs needs to be validated the respective stakeholders (HR, Finance, Production)
| 12.4 | Deploy the dashboard to production
| 12.5 | Create a detailed Document Acting as User Manual & Provide a detailed Semantic Model Description & Metadata Glossary | [9 empty] | Alignment on the dashboards have not yet happened
High-Level Data Governance Plan | 13 | Develop a high-level data governance plan outlining key aspects : Data Ownership Data Access Control Data quality standards Data security Measures Data Retention & Archiving | [9 empty] | Checklist for SOP Walkthrough is complete and to be shared with Mr.Prudhvi
| 13.1 | Finalize & Implement the Data Governance Plan | [9 empty] | Understanding the "As-is" process is very difficult as there is limited cross- functional input deliberation
ERP Evaluation Checklist | 14 | Create a well defined and scalable ERP evaluation checklist that details function wise good to have and must have features in aspects of Business needs & goals, Functional requirements, Technical specifications, User experience & interface, Security & Compliance, Cost & licensing, Long term support & sustainability
Integrated Email Infrastructure Plan | 15 | Devise a plan for centralized email infrastructure setup
| 15.1 | Define Email Access and Permission Management
| 15.2 | Set up secure email protocols (encryption, spam filters)
| 15.3 | Develop company-wide email usage policies (e.g., signature formats, response times)
IPO Advisory Value Add Services | 16 | Investor Story Effectiveness Checklist
| 16.1 | Standard template for reporting of position of working capital
| 16.2 | Standard Reporting Checklist for Post IPO Reporting for Fund allocation
| 16.3 | Redefined Data Capture template for daily production and movement of Palm Oil
Org chart Proposal for Upcoming factories (Rice & Pulses Mill) | 17.1 | Understanding the requirements from the stakeholders to define production capacity, timelines, procurement plans, Machinery details, shift details | [10 empty] | New addition
| 17.2 | Visiting the factory setup and understanding the production process and workforce requirement
| 17.3 | Identify roles needed across departments and categories as per stand alone and shared service departments
| 17.4 | Research work - Understand the org chart in similar production units, recruitment agencies, Naukri & other sources
| 17.5 | Pen down an org chart capturing all the above requirements/inputs and considering rice production 450MT/ per day / 20hrs & Pulses 340mt/per day/ 20hrs
| 17.6 | Submit the Org Chart Proposal to the Mgmt
| 17.7 | Script - Skill sets, qualification, no.of emp, job role, salary range, hiring timeline for each of the role mentioned in the org chart
| 17.8 | Review it with Flipcarbon team
| 17.9 | Submit the final Org chart proposal for review
Monthly Financial Reporting | 18.1 | Gather and verify financial data from all departments.
| 18.2 | Prepare draft reports (P&L, Balance Sheet, Cash Flow) with variance analysis.
| 18.3 | Conduct internal review meetings and finalize reports.
| 18.4 | Present reports to leadership with actionable insights.
Financial Planning & Forecasting | 19.1 | Analyze historical data and gather input for forecasts.
| 19.2 | Create baseline, best-case, and worst-case scenarios.
| 19.3 | Present forecasts for feedback and refine them.
| 19.4 | Finalize the plan and align it with strategic goals.
SOP Monitoring | 20.1 | Deploy SOPs to all teams and ensure accessibility on internal platforms.
| 20.2 | Conduct training sessions to familiarize teams with SOPs and expected outcomes.
| 20.3 | Establish compliance checkpoints to track adherence and measure KPIs.
| 20.4 | Identify and address deviations through root cause analysis and corrective actions.
| 20.5 | Collect feedback and refine SOPs for continuous improvement.
IPO Project Management | 21.1 | Schedule and conduct an initial call with Narnolia, the merchant banker, to outline the IPO process and expectations.
| 21.2 | Establish a coordination framework for internal teams and external advisors (legal, financial, and marketing).
| 21.3 | Facilitate collaboration across teams, ensuring timely delivery of inputs and responses to merchant banker queries.
| 21.4 | Designing and preparing the annual report
Treasury Management | 22.1 | Assess cash flow and create a short-term liquidity plan.
| 22.2 | Identify investment opportunities for surplus funds.
| 22.3 | Implement treasury management systems and controls.
| 22.4 | Monitor debt obligations and optimize repayment strategies.
Market Research | 23.1 | Define target markets and customer segments
| 23.2 | Analyze competitor offerings, pricing, and positioning in domains of Rices, pulses, oil, spices (trading)
| 23.3 | Identify industry trends and emerging opportunities
| 23.4 | Compile insights into a comprehensive report for strategic decision-making
Management Routines | 24.1 | Create and establish a recurring meeting schedule with clear agendas for leadership alignment.
| 24.2 | Implement systems to monitor and track key performance indicators (KPIs).
| 24.3 | Facilitate decision-making through structured updates and progress reviews.
| 24.4 | Document and follow up on action points from meetings to ensure accountability.
D2C for Akshayam | 25.1 | Develop a direct-to-consumer strategy tailored to Akshayam's brand and target audience.
| 25.2 | Build an e-commerce platform and integrate payment and logistics solutions.
| 25.3 | Implement a digital marketing campaign to drive traffic and customer acquisition.
| 25.4 | Monitor sales, customer feedback, and adjust offerings for continuous improvement.
Investor Relationship Management Post IPO | 25.1 | Establish a dedicated investor relations team and communication framework.
| 25.2 | Create a calendar of regular updates, including quarterly earnings calls and annual reports.
| 25.3 | Engage with analysts, institutional investors, and retail shareholders to address inquiries.
| 25.4 | Monitor shareholder feedback and market sentiment to guide future strategies.